## WBS
# | Task | Est.Effort (hour)
1 | Investigate specs of Weather API Service following requirements | 2
2 | Write sample code to get data from Weather APIs | 2
3 | Select tech & design system architecture | 2
4 | Design DB schema | 2
5 | Create project structure & setup general components | 2
6 | Implement back-end code to extract data from Weather APIS following design | 10
7 | Implement simple GUI to show results as requirements | 2
8 | Create a simple all-in-one deployment | 2
9 | Write document to introduce the source code, architecture, how to deploy, next development | 4
10 | Backup time | 4